## Workshop Plan
Session | Planned Date | Objective | Duration | Methodology | Key Participants |  | Workshop Type | Topics Covered | Methodology / Process | Mode of Execution | Primary Deliverable | Inputs Required | Expected Outputs | Exit Criteria | BR Lead | DDIT Lead | CTS Lead | Quality Lead | Security Lead | BFF Lead
Session 1 | 2026-08-03 | Establish a single agreed portfolio baseline and transition scope | 2.5 Hrs | Offline data gathering completed before workshop. Workshop focused on validation, classification and approval. | BR Leadership, DDIT Leads, CTS Lead, BFFs, App Owners | Sudheer + Joydip | Validation & Decision | Application Inventory, Ownership, Business Functions, User Base, GxP Classification, Business Criticality, Operational Complexity, Lifecycle Status, Documentation Maturity, Transition Priority, Special Handling Requirements | Review portfolio baseline → validate ownership → validate classifications → identify exceptions → align transition scope → approve portfolio baseline | Facilitated portfolio review | Application Portfolio Baseline | Application inventory, ownership tracker, application metadata, initial classifications, current SOW scope | Approved application portfolio baseline, ownership matrix, classification matrix, transition priority list, scope issue log | Every application classified, ownership agreed, transition priority assigned, scope baseline approved | rkshop
Session 2 | 2026-08-05 | Understand and document the current-state operating model across all in-scope applications | 2 Hrs | BR presents current operating model, support processes, pain points, vendor challenges and operational realities. Focus is understanding current state, not solution design. | BR Ops, DDIT Ops, CTS Ops, Key SMEs |  | Discovery & Validation | Support Model, Incident Management, Problem Management, Service Requests, Change Management, Release Management, Escalation Process, SLA/KPI Baseline, Current Tooling Landscape | Current-state walkthrough → process assessment → pain-point analysis → identify operational dependencies and support gaps | Process discovery workshop | Current Operations Baseline | Support documentation, ITSM processes, SLA reports, ticket volumes, support roster, tooling inventory | Current-state support model, support ownership map, operational dependency register, operational gap list | Current operating model fully understood and documented
Session 3 | 2026-08-10 | Define future-state DDIT operating model and transition blueprint leveraging the ongoing CTS onboarding | 4 Hrs | DDIT presents target operating model. CTS presents how current onboarding aligns/misaligns with DDIT ways of working. Focus on designing target state and minimizing rework. | DDIT Ops, CTS Ops, BR Ops |  | Design & Decision | DDIT Support Model, Service Ownership Model, Tooling Standards, CMDB, Knowledge Transfer, Shadow Support, Reverse Shadow, Transition Waves, Readiness Criteria, Hypercare | Future-state review → current vs future gap analysis → identify CTS adjustments required → define transition approach → define ownership model | Collaborative design workshop | Operations Transition Blueprint | Outputs from Session 2, DDIT standards, CTS onboarding model, service management standards | Approved future-state operating model, KT approach, support ownership model, transition wave strategy, readiness criteria, hypercare model | DDIT target model approved and operation transition strategy agreed
Session 4 | 2026-08-13 | Establish application architecture, technical landscape and dependency baseline | 2 Hrs | CTS performs offline discovery and presents findings. Workshop validates dependencies and ownership. | CTS AMs, App SMEs, BR, DDIT Architecture Leads |  | Technical Review | Architecture, Infrastructure, Environments, Hosting, Databases, Integrations, Authentication, Technical Debt, End-of-Life Components, Technical Dependencies | CTS presentation → dependency validation → ownership confirmation → technical risk identification | Technical review workshop | Technical & Dependency Baseline | Architecture diagrams, hosting details, integration maps, infrastructure information | Technical dependency map, ownership matrix, technical risk register, technical debt register | No critical technical dependency remains unknown
Session 5 | 2026-08-17 | Assess compliance, quality and inspection readiness posture | 3 Hrs | CTS presents compliance assessment, findings and observations. Quality validates and prioritizes. | BR, DDIT, CTS, Quality, eCompliance, ISRM |  | Assessment & Decision | GxP Classification, CSV, SDLC, Validation Status, SOP Alignment, Audit Findings, CAPAs, Deviations, Inspection Readiness, Periodic Reviews, Compliance Ownership Model | Compliance baseline review → evidence assessment → gap identification → impact assessment → ownership discussion | Quality-led workshop | Compliance & Quality Baseline | Validation package, audit reports, CAPA tracker, SOP inventory, quality assessments | Compliance baseline, compliance gap register, inspection readiness assessment, audit risk profile | Compliance position and ownership model understood and accepted
Session 6 | 2026-08-18 | Assess security, privacy and information risk readiness | 2 Hrs | CTS and ISRM present current security posture and identified risks. Focus on transition implications and DDIT control alignment. | BR, DDIT, CTS, ISRM, Security |  | Assessment & Decision | Security Classification, Access Management, Vendor Access, Privileged Access, Vulnerabilities, Patch Management, Logging, Monitoring, Data Privacy, Security Exceptions, Security Control Alignment | Security review → control assessment → risk classification → DDIT security alignment review | Security assessment workshop | Security & Privacy Baseline | Security assessments, vulnerability scans, access reviews, data classification inventory | Security baseline, security risk register, security remediation requirements, DDIT control alignment actions | Security risks categorized and ownership agreed
Session 7 | 2026-08-20 | Review products, services and contract ownership model | 2 Hrs | Review current contractual landscape and identify changes required to align CTS under DDIT ownership. | BR Vendor Mgmt, DDIT Vendor Mgmt, CTS, Procurement |  | Validation & Decision | Product Ownership, Service Ownership, Existing Contracts, Vendor Responsibilities, Current SOW Scope, Future DDIT Ownership Model, Contractual Gaps | Contract review → ownership review → identify commercial gaps → align future ownership model | Commercial review workshop | Target Ownership & Contract Baseline | Existing SOWs, contracts, ownership details, vendor obligations | Contract gap assessment, ownership alignment model, SOW transition implications | Future ownership and vendor accountability model understood
Session 8 | 2026-08-24 | Validate the complete operations transition approach and transition readiness | 2 Hrs | Consolidated review of outputs from Sessions 1–7. Focus on alignment and approval. | BR, DDIT, CTS Leadership Team |  | Validation & Approval | Transition Waves, Service Ownership, KT Plan, Tooling Approach, DDIT Readiness, Operational Readiness, Hypercare, Acceptance Criteria | Consolidated review → challenge assumptions → resolve gaps → approval discussion | Alignment workshop | Approved Operations Transition Plan | Outputs from Sessions 1–7 | Approved operations transition roadmap, readiness plan, ownership model | Operations transition strategy approved for execution
Session 9 | 2026-08-26 | Prepare stakeholders and business for transition | 2 Hrs | OCM team presents findings and proposed adoption approach. | BR, CTS, DDIT, BFFs, OCM Leads |  | Planning & Validation | Stakeholder Mapping, Impact Assessment, Communications, Training, Adoption, Readiness, Business Continuity, Hypercare Support Model | Stakeholder mapping → impact assessment → communication plan review → training readiness review | OCM workshop | OCM & Business Readiness Plan | Stakeholder inventory, business calendars, organizational structures | Approved OCM plan, training strategy, communication plan, adoption approach, continuity considerations | Stakeholder onboarding and adoption approach approved
Session 10 | 2026-08-28 | Assess commercial, budget and vendor implications | 2 Hrs | Review current contracts, run costs, project costs, remediation costs and ownership changes. | BR Finance, DDIT Finance, CTS, Procurement |  | Commercial Review | SOW Review, Vendor Model, Contractual Gaps, Budget Assumptions, Resource Requirements, Licensing, Funding Ownership, Future Run Costs | Commercial assessment → funding assessment → resource planning → ownership alignment | Commercial and finance workshop | Budget, Vendor & Commercial Plan | Contracts, rate cards, resource assumptions, funding details | Budget assumptions, commercial model, resource plan, vendor alignment plan | Funding and commercial impacts understood and agreed
Session 11 | 2026-08-31 | Establish future-state governance and operating model | 3 Hrs | DDIT presents future governance model with CTS operating under DDIT governance. | DDIT, BR, CTS Leadership |  | Governance & Approval | RACI, Governance Forums, Decision Rights, Escalation Model, Acceptance Criteria, Reporting Model, Success Criteria, Compliance Governance, Service Governance, Portfolio Governance | Governance design → RACI review → decision rights review → operating model approval | Leadership workshop | Future Governance & Operating Model | Outputs from prior sessions | Future operating model, governance framework, reporting structure, acceptance criteria, governance cadence | Future-state BR-DDIT-CTS governance approved
Session 12 | 2026-09-07 | Define remediation strategy and execution model | 4 Hrs | DDIT presents proposed remediation execution model leveraging CTS capabilities and future DDIT governance. | DDIT, BR, Quality, eCompliance, ISRM, CTS |  | Planning & Decision | Operational Gaps, Compliance Gaps, Security Gaps, Documentation Gaps, Process Gaps, Tooling Gaps, Infrastructure Gaps, Remediation Ownership, Residual Risk Management | Gap consolidation → prioritization → blocker identification → ownership assignment → roadmap approval | Remediation planning workshop | Remediation Program | Outputs from Sessions 2–6 | Remediation roadmap, remediation ownership model, execution plan, residual risk approach, governance model | Every identified gap assigned owner, priority, execution path and target timeline
Session 13 | 2026-09-08 | Define ownership transition approach for ongoing, in-flight and planned initiatives, and establish the future demand intake model | 3 Hrs | DDIT to present the proposed delivery ownership and future intake approach. BR to present current initiative portfolio, priorities and business context. Session focused on agreeing the transition path for each initiative and future governance model. | DDIT Delivery Lead, BR Portfolio/Delivery Leads, CTS Delivery Lead, Business Sponsors, BFFs, Quality/eCompliance, ISRM as needed | Amrendra Singh | Portfolio & Decision | Ongoing Initiatives, In-flight Initiatives, Planned Initiatives, Enhancement Backlog, Delivery Ownership, Future Demand Intake, Prioritization Model, Project Governance, Delivery Acceptance Criteria | Portfolio review → initiative categorization → ownership assessment → dependency review → transition decision per initiative → future intake process design | Delivery and portfolio workshop | Initiative Transition & Future Intake Model | Initiative portfolio, project plans, demand backlog, enhancement backlog, current governance process, funding status, vendor dependencies, business priorities | Initiative Transition Plan, Delivery Ownership Model, Future Intake Process, Initiative Decision Log, Future Demand Governance Model | Transition approach defined for every initiative; DDIT delivery ownership model agreed; BR business prioritization role confirmed; future demand intake process approved

## Scope & Inventory
Sl No | Planned Date | Topic | Topic Category | Description / Details Needed | Workshop Discussion Focus | Upfront Data to Gather | Data Source / Location | Dependency / Pre-requisite | Primary Owner | Supporting Teams | Stakeholders Required for Workshop | How Discussion Will Be Run | Expected Output | Primary SME | Backup SME | Availability | Decision Required | Decision Owner | Risk if Delayed | Knowledge Artifact for Agent | Status | Comments
1 | 2026-07-20 | Application master list | Scope | Full list of ~40 applications | Confirm complete application universe and alignment to BR-CTS scope | Existing app inventory, SOW list, app IDs, aliases | BR-CTS SOW / App inventory / Portfolio tracker | Pre-work app list available | BR | DDIT, CTS | BR Ops, BFFs, App SMEs, CTS, DDIT | Walk through application list and mark in-scope / out-of-scope / unclear | Validated application inventory | TBD | TBD | TBD | Yes | BR/DDIT Leads | Scope ambiguity impacts all WS execution | Application metadata | Not Started
2 | 2026-07-20 | Application ownership | Scope | Business owner, BR owner, IT owner, SME | Confirm current and future ownership clarity | Existing ownership details, app owner list | Ownership tracker / SharePoint / App register | Application master list confirmed | BR | DDIT | BR Ops, BFFs, Business Owners, App SMEs, DDIT | App-by-app ownership validation | Ownership baseline | TBD | TBD | TBD | Yes | BR/DDIT Leads | Ownership gaps delay transition acceptance | Ownership graph | Not Started
3 | 2026-07-20 | Business function supported | Scope | Business process supported by each app | Understand business purpose and dependency | Process description, user groups, business function | Business process docs / SME inputs | Application list confirmed | BR | Business SMEs | Business Owners, BFFs, App SMEs | Discuss business use and process dependency | Business function mapping | TBD | TBD | TBD | No | BR Business Owner | Business impact may be misclassified | Business capability map | Not Started
4 | 2026-07-20 | User base and usage | Scope | User groups, usage volume, geography, business dependency | Understand who uses the app and how critical usage is | User list, user groups, usage frequency | App admin data / Access lists / Business inputs | Application list confirmed | BR | CTS, DDIT | Business Owners, App SMEs, BR Ops | Capture usage and dependency profile | Usage and impact profile | TBD | TBD | TBD | No | BR Business Owner | Business continuity risk may be underestimated | Usage profile | Not Started
5 | 2026-07-20 | GxP / clinical relevance | Compliance | GxP critical, GxP supporting, clinical, non-GxP | Validate regulated relevance and inspection sensitivity | GxP classification, validation status, quality assessment | Quality repository / Validation tracker | Application list confirmed | BR | Quality, DDIT | Quality, eCompliance, App SMEs, Business Owners | App-by-app review with Quality input | Regulatory classification | TBD | TBD | TBD | Yes | Quality/eCompliance | Wrong classification creates compliance risk | Regulatory classification knowledge | Not Started
6 | 2026-07-20 | Business criticality | Scope | High / medium / low criticality | Assess business impact if unavailable | Business impact, workarounds, critical windows | BCP docs / Business inputs | Business function mapping available | BR | Business Owners | Business Owners, BFFs, App SMEs | Rate impact and agree criticality | Business criticality rating | TBD | TBD | TBD | Yes | BR Business Owner | Wrong wave sequencing or risk priority | Criticality model | Not Started
7 | 2026-07-20 | Operational complexity | Operations | Support complexity, integrations, vendor dependency | Assess how complex each app is to transition/support | Support model, integrations, tickets, known issues | Ops tracker / Ticketing tools / CTS input | Application list confirmed | DDIT | BR, CTS | BR Ops, CTS, DDIT Ops, App SMEs | Review complexity drivers per application | Operational complexity rating | TBD | TBD | TBD | Yes | DDIT Ops Lead | Transition effort may be underestimated | Operational complexity profile | Not Started
8 | 2026-07-20 | Documentation maturity | Compliance | Availability of operational, technical, CSV, SDLC docs | Check available/missing documents | Document repository links, runbooks, SOPs, validation docs | SharePoint / Vault / Quality repository | Application list confirmed | BR | Quality, CTS, DDIT | App SMEs, Quality, CTS, BR Ops | Review evidence availability and mark maturity | Documentation maturity view | TBD | TBD | TBD | No | Quality/BR Ops | Remediation scope may be missed | Documentation inventory | Not Started
9 | 2026-07-20 | Lifecycle status | Scope | Active, stable, enhanced, retirement, limited use | Understand lifecycle stage | Product roadmap, retirement plans, enhancement status | Product roadmap / Portfolio tracker | Application list confirmed | BR | DDIT | App SMEs, Business Owners, DDIT | Confirm lifecycle status and transition implication | Lifecycle categorization | TBD | TBD | TBD | Yes | BR/DDIT Leads | Apps may transition despite retirement/major change | Lifecycle status knowledge | Not Started
10 | 2026-07-20 | Transition priority | Scope | Prioritization for transition wave planning | Decide earlier/later focus based on risk | Criticality, compliance risk, operational complexity | Classification matrix | Topics 1–9 completed | DDIT | BR, Quality | BR Ops, DDIT, Quality, Business Owners | Risk-based prioritization discussion | Initial transition priority | TBD | TBD | TBD | Yes | DDIT/BR Leads | Wave plan cannot be finalized | Transition priority model | Not Started
11 | 2026-07-20 | Special handling needs | Scope | Apps needing unique handling | Identify exceptions due to risk, timing, compliance, dependency | Known constraints, blackout dates, vendor restrictions | App SMEs / Business calendar / Vendor inputs | Transition priority drafted | BR | DDIT, CTS, Quality | App SMEs, Quality, Security, DDIT, CTS | Capture exception conditions | Special handling list | TBD | TBD | TBD | Yes | BR/DDIT Leads | Critical exceptions may be missed | Exception register | Not Started
12 | 2026-07-20 | Scope gaps and unknowns | Scope | Missing data or unclear scope items | Identify unresolved data gaps and assign owners | Tracker fields marked unknown/TBD | Master tracker | Topics 1–11 reviewed | BR | PMO, DDIT, CTS | All workstream leads | Review open gaps and assign owners | Data gap log | TBD | TBD | TBD | Yes | PMO/BR Lead | Workshops proceed with incomplete data | Data gap register | Not Started

## Operations Lift-and-Shift Trans
Sl No | Planned Date | Topic | Topic Category | Description / Details Needed | Workshop Discussion Focus | Upfront Data to Gather | How Discussion Will Be Run | Data Source / Location | Dependency / Pre-requisite | Primary Owner | Supporting Teams | Stakeholders Required for Workshop | Expected Output | Primary SME | Backup SME | Availability | Decision Required | Decision Owner | Risk if Delayed | Knowledge Artifact for Agent | Status | Comments
13 | 2026-07-21 | Current support model | Operations | L1/L2/L3, BR/CTS/vendor responsibilities | Understand current support model | Support docs, contacts, current RACI | App cluster-based walkthrough | Support docs / CTS inputs / Jira/SNOW | Application inventory available | BR | CTS, DDIT | BR Ops, CTS, App SMEs | Current support baseline | TBD | TBD | TBD | No | BR Ops | Target model may be designed incorrectly | Current service model | Not Started
14 | 2026-07-21 | Incident management | Operations | Incident intake, triage, escalation, resolution | Define incident flow post-transition | Incident process, recent examples, severity matrix | Process walkthrough and gap mapping | Jira/SNOW / Incident reports | Current support model available | DDIT | BR, CTS | BR Ops, CTS, DDIT Ops | Incident transition requirements | TBD | TBD | TBD | Yes | DDIT Ops | Service continuity risk | Incident process knowledge | Not Started
15 | 2026-07-21 | Problem management | Operations | RCA and recurring issue management | Define future problem ownership | Problem records, recurring issue data, RCA examples | Review recurring issues and ownership | Jira/SNOW / RCA docs | Current support model available | DDIT | CTS, BR | BR Ops, CTS, DDIT Ops | Problem management model | TBD | TBD | TBD | Yes | DDIT Ops | Recurring issues may continue unresolved | Problem management knowledge | Not Started
16 | 2026-07-21 | Service request management | Operations | Standard user/business requests | Define request routing and fulfillment model | Service catalog, common request types | Review request types and routing | Service catalog / Jira/SNOW | Current support model available | DDIT | BR, CTS | BR Ops, CTS, DDIT Service Mgmt | Service request model | TBD | TBD | TBD | Yes | DDIT Service Mgmt | Users may continue using wrong channels | Service request catalog | Not Started
17 | 2026-07-21 | Change management | Operations / Compliance | Application/infrastructure change process | Define change ownership and approvals | Change records, CAB process, change calendar | Map current vs future change flow | Jira/SNOW / CAB records / Quality docs | GxP classification available | DDIT | Quality, BR, CTS | BR Ops, DDIT, CTS, Quality | Change governance model | TBD | TBD | TBD | Yes | DDIT + Quality | Uncontrolled changes/compliance risk | Change process knowledge | Not Started
18 | 2026-07-21 | Release management | Operations / Delivery | Release planning, deployment, approvals | Define release ownership and evidence needs | Release calendar, deployment SOPs, release notes | Review release lifecycle | Release docs / Project repos | Change process reviewed | DDIT | BR, CTS, Quality | App SMEs, CTS, DDIT Delivery, Quality | Release ownership model | TBD | TBD | TBD | Yes | DDIT Delivery | Release governance gaps | Release management knowledge | Not Started
19 | 2026-07-21 | Escalation model | Operations | Operational escalation route | Define severity-based escalation | Escalation contacts, historical examples | Scenario-based escalation review | Support docs / Incident history | Incident model reviewed | DDIT | BR, CTS | BR Ops, DDIT, CTS, Business Owners | Escalation matrix | TBD | TBD | TBD | Yes | DDIT Ops | Slow response during cutover | Escalation graph | Not Started
20 | 2026-07-21 | SLA/OLA/KPI baseline | Operations | Service expectations and reporting | Define service levels and metrics | SLA data, ticket volumes, reports | Agree future service expectations | Jira/SNOW reports / CTS reports | Incident/service request models reviewed | DDIT | CTS, BR | DDIT Ops, CTS, BR Ops, Business | SLA/KPI baseline | TBD | TBD | TBD | Yes | DDIT Ops | No measurable service acceptance | Service KPI model | Not Started
21 | 2026-07-22 | Future DDIT support model | Operations | DDIT ownership, CTS role, BR role | Define target operational model | DDIT support standards, managed service model | Compare current vs target model | DDIT operating model docs | Current ops baseline complete | DDIT | BR, CTS | DDIT Ops, CTS, BR Ops | Target support model | TBD | TBD | TBD | Yes | DDIT Lead | Oct 1 ownership unclear | Target operating model | Not Started
22 | 2026-07-22 | Tooling transition | Operations / Tooling | Jira, SNOW, email, Teams, other tools | Define target service management tooling | Tool list, queues, categories, reports | Review current vs target ticketing | Jira/SNOW / Tool inventory | Current support model complete | DDIT | BR, CTS | DDIT Service Mgmt, CTS, BR Ops | Tooling transition approach | TBD | TBD | TBD | Yes | DDIT Service Mgmt | Support routing/reporting gaps | Tooling knowledge artifact | Not Started
23 | 2026-07-22 | CMDB/service records | Operations / Tooling | Application-service metadata | Define records required for ownership | CMDB data, app/service IDs, owner info | Validate service metadata needs | SNOW CMDB / App inventory | Application inventory validated | DDIT | BR, CTS | DDIT Service Mgmt, CTS, BR Ops | CMDB readiness requirements | TBD | TBD | TBD | Yes | DDIT Service Mgmt | Incorrect routing/ownership | CMDB metadata | Not Started
24 | 2026-07-22 | KT requirements | Operations | Knowledge required for handover | Define technical and functional KT needs | SME list, current docs, support topics | Define KT scope by app/category | Runbooks / SME input / Ticket history | Current support model complete | BR | DDIT, CTS | BR SMEs, CTS, DDIT | KT plan | TBD | TBD | TBD | Yes | BR/DDIT Leads | DDIT not ready to operate | KT knowledge package | Not Started
25 | 2026-07-22 | Shadow and reverse shadow | Operations | Handover support approach | Define observe/perform/own sequence | Support calendar, ticket examples, SME availability | Define handover sequence | Support tracker / Ticketing tools | KT scope defined | DDIT | BR, CTS | BR Ops, CTS, DDIT | Shadow/reverse shadow plan | TBD | TBD | TBD | Yes | DDIT Ops | Handover quality risk | Handover model | Not Started
26 | 2026-07-22 | Cutover readiness | Operations | Minimum readiness for Oct 1 | Define readiness gates for ownership | Draft readiness checklist | Agree go/no-go criteria | Program tracker | Target support model drafted | DDIT | BR, CTS, Quality, Security | DDIT, BR Ops, CTS, Quality, Security | Cutover readiness checklist | TBD | TBD | TBD | Yes | DDIT/Quality | Oct 1 readiness cannot be confirmed | Readiness criteria | Not Started
27 | 2026-07-22 | Hypercare/stabilization | Operations / OCM | Post-Oct 1 support approach | Define handholding, issue tracking, review cadence | Risk areas, support availability | Define stabilization model | OCM plan / Support model | Cutover readiness drafted | DDIT | BR, CTS | DDIT, CTS, BR Ops, Business | Hypercare plan | TBD | TBD | TBD | Yes | DDIT Ops | Post-cutover instability | Hypercare playbook | Not Started

## Architecture & Technical Landsc
Sl No | Planned Date | Topic | Topic Category | Description / Details Needed | Workshop Discussion Focus | Upfront Data to Gather | Data Source / Location | Dependency / Pre-requisite | Primary Owner | Supporting Teams | Stakeholders Required for Workshop | How Discussion Will Be Run | Expected Output | Primary SME | Backup SME | Availability | Decision Required | Decision Owner | Risk if Delayed | Knowledge Artifact for Agent | Status | Comments
28 | 2026-07-23 | Application architecture | Architecture | High-level architecture per app | Understand architecture and operational dependencies | Architecture diagrams, app overview | EA repository / SharePoint / Confluence | Application inventory validated | DDIT | BR, CTS | Architects, App SMEs, DDIT, CTS | Architecture walkthrough | Architecture baseline | TBD | TBD | TBD | No | DDIT Architecture | Unknown architecture impacts support | Architecture knowledge | Not Started
29 | 2026-07-23 | Infrastructure ownership | Architecture | Server/cloud/platform ownership | Confirm hosting and infrastructure responsibility | Infra inventory, server list, cloud accounts | Infra CMDB / Cloud console / SNOW | Architecture baseline available | DDIT | Infra, CTS | Infra, DDIT, CTS, App SMEs | Dependency review | Infrastructure ownership map | TBD | TBD | TBD | Yes | DDIT Infra | Ownership gaps in production support | Infra ownership artifact | Not Started
30 | 2026-07-23 | Environment ownership | Architecture | Dev/Test/UAT/Prod ownership | Clarify environment responsibility and support | Environment list, access model | App docs / Infra docs | Infrastructure ownership available | DDIT | BR, CTS | DDIT, BR SMEs, CTS | Environment-by-environment review | Environment ownership map | TBD | TBD | TBD | Yes | DDIT | Release/support issues | Environment map | Not Started
31 | 2026-07-23 | Database ownership | Architecture | DB technology, ownership, access, backup | Confirm database support model | DB inventory, DBA contacts, backup details | DB inventory / Infra docs | App architecture available | DDIT | Infra, CTS | DBAs, Infra, CTS, App SMEs | DB dependency review | Database ownership map (IAS resource) | TBD | TBD | TBD | Yes | DDIT Infra | Data/support risk | DB knowledge artifact | Not Started
32 | 2026-07-23 | Hosting model | Architecture | Cloud/on-prem/SaaS/vendor hosted | Confirm hosting and operational responsibility | Hosting details, vendor hosting contracts | CMDB / Vendor docs | App inventory available | DDIT | BR, CTS, Procurement | Infra, DDIT, CTS, App SMEs | Hosting model review | Hosting baseline | TBD | TBD | TBD | No | DDIT Infra | Wrong support routing | Hosting knowledge | Not Started
33 | 2026-07-23 | Integration landscape | Architecture | Interfaces and dependencies | Identify upstream/downstream risks | Interface list, data flows, integration diagrams | Interface repository / App docs | Architecture baseline available | DDIT | BR, Security, CTS | Architects, SMEs, Security, CTS | Integration walkthrough | Dependency register | TBD | TBD | TBD | Yes | DDIT Architecture | Hidden dependency risk | Integration graph | Not Started
34 | 2026-07-23 | Authentication model | Architecture / Security | SSO/MFA/local accounts/AD groups | Understand login and identity integration | Auth diagrams, AD groups, local account list | IAM tools / Security docs | App inventory validated | DDIT | Security, BR | Security, Infra, App SMEs | Identity model review | Authentication baseline | TBD | TBD | TBD | No | Security/DDIT | Access/security gaps | Identity model artifact | Not Started
35 | 2026-07-23 | Technical debt | Architecture / Delivery | Known technical debt, EOL, obsolescence | Identify risk and ownership for remediation/project work | Tech debt list, EOL status, platform versions | App roadmap / Infra tracker | Architecture baseline available | DDIT | BR, CTS, Security | DDIT Tech, CTS, App SMEs, Security | Categorize debt by risk/ownership | Technical debt register | TBD | TBD | TBD | Yes | DDIT | Hidden cost/remediation risk | Tech debt knowledge | Not Started

## Quality, Compliance, Security &
Sl No | Planned Date | Topic | Topic Category | Description / Details Needed | Workshop Discussion Focus | Upfront Data to Gather | Data Source / Location | Dependency / Pre-requisite | Primary Owner | Supporting Teams | Stakeholders Required for Workshop | How Discussion Will Be Run | Expected Output | Primary SME | Backup SME | Availability | Decision Required | Decision Owner | Risk if Delayed | Knowledge Artifact for Agent | Status | Comments
36 | 2026-07-24 | CSV status | Compliance | Validation status and evidence availability | Identify validation readiness and gaps | Validation plan/report, URS, test evidence | Quality repository / Validation folder | GxP classification complete | BR | Quality, DDIT | CSV SMEs, Quality, App SMEs | Artifact availability review | CSV readiness baseline | TBD | TBD | TBD | Yes | Quality | Audit/inspection risk | Validation knowledge | Not Started
37 | 2026-07-24 | SDLC artifacts | Compliance / Delivery | Requirements, design, test, release docs | Identify missing lifecycle documentation | Requirements, design, test, release docs | SharePoint / Jira / Confluence | App inventory complete | BR | Quality, CTS, DDIT | App SMEs, BR Delivery, CTS, Quality | Document checklist review | SDLC gap register | TBD | TBD | TBD | No | BR/Quality | Remediation scope incomplete | SDLC artifact inventory | Not Started
38 | 2026-07-24 | Audit findings | Compliance | Findings, observations, CAPAs | Review open/closed findings and transition impact | Audit reports, CAPA tracker, observations | Audit tracker / Quality system | GxP apps identified | BR | Quality, DDIT | Quality, Compliance, App SMEs | Findings walkthrough | Audit finding register | TBD | TBD | TBD | Yes | Quality | Open findings not managed in transition | Audit findings knowledge | Not Started
39 | 2026-07-24 | Deviation/CAPA management | Compliance | Deviations and corrective actions | Confirm ownership and closure timeline | Deviation/CAPA records | Quality system | Audit findings available | BR | Quality, DDIT | Quality, App SMEs, BR Ops, DDIT | Review open actions and impact | CAPA transition plan | TBD | TBD | TBD | Yes | Quality | CAPA ownership ambiguity | CAPA knowledge | Not Started
40 | 2026-07-24 | SOP alignment | Compliance / Operations | Alignment to approved processes | Check whether operations follow required SOPs | SOP list, process maps | Quality docs / SOP repository | Operations baseline available | BR | Quality, DDIT, CTS | Quality, BR Ops, DDIT, CTS | Compare actual vs expected process | SOP gap list | TBD | TBD | TBD | No | Quality | Process non-compliance | SOP mapping artifact | Not Started
41 | 2026-07-24 | Inspection readiness | Compliance | Ability to support inspection | Confirm evidence availability and owner readiness | Inspection history, evidence folders | Quality repository | CSV/SDLC/audit review started | BR | Quality, DDIT, CTS | Quality, App SMEs, DDIT, CTS | Readiness review for high-risk apps | Inspection readiness view | TBD | TBD | TBD | Yes | Quality | Inspection response risk | Inspection readiness knowledge | Not Started
42 | 2026-07-24 | Periodic review status | Compliance | Periodic review completion | Identify overdue/missing reviews | Periodic review reports | Quality repository | GxP classification complete | BR | Quality, DDIT | Quality, App SMEs, DDIT | Review required vs completed | Periodic review tracker | TBD | TBD | TBD | No | Quality | Compliance evidence gap | Periodic review knowledge | Not Started
43 | 2026-07-28 | Remediation classification | Remediation | Gap prioritization | Classify gaps as blocker/high/post-transition/BAU | Gap list from assessments | Gap tracker | Compliance/security/ops gaps available | DDIT | BR, Quality, CTS | Quality, DDIT, BR, CTS | Risk-prioritization discussion | Remediation categorization | TBD | TBD | TBD | Yes | Quality/DDIT | Wrong blockers or missed remediation | Remediation backlog | Not Started
44 | 2026-07-28 | Remediation ownership | Remediation | Owner and timeline for each gap | Assign BR/DDIT/CTS/Quality ownership | Gap register, ownership assumptions | Remediation tracker | Remediation categories defined | DDIT | BR, Quality, CTS | Quality, BR, DDIT, CTS | Assign owner and due date | Remediation RACI | TBD | TBD | TBD | Yes | DDIT/Quality | Remediation execution stalls | Remediation ownership model | Not Started
45 | 2026-07-28 | Residual risk acceptance | Remediation / Governance | Risks continuing after Oct 1 | Decide what can continue post-transition and approval path | Risk register, mitigation proposal | RAID / Quality risk log | Remediation ownership defined | DDIT | BR, Quality | Quality, DDIT, BR Leadership | Decision-based risk discussion | Residual risk log | TBD | TBD | TBD | Yes | Quality/Leadership | Unapproved compliance risk | Residual risk artifact | Not Started

## Security, Information Risk, Dat
Sl No | Planned Date | Topic | Topic Category | Description / Details Needed | Workshop Discussion Focus | Upfront Data to Gather | Data Source / Location | Dependency / Pre-requisite | Primary Owner | Supporting Teams | Stakeholders Required for Workshop | How Discussion Will Be Run | Expected Output | Primary SME | Backup SME | Availability | Decision Required | Decision Owner | Risk if Delayed | Knowledge Artifact for Agent | Status | Comments
46 | 2026-07-27 | Information security classification | Security | Security/data classification of apps | Confirm sensitivity and information risk | Data classification records | Security repository / App tracker | Application inventory complete | DDIT | BR, Security | Security/ISC, App SMEs, Business | Confirm classification by app | Security classification baseline | TBD | TBD | TBD | Yes | Security | Security risk misclassified | Security classification knowledge | Not Started
47 | 2026-07-27 | Data classification | Security / Privacy | Type of data processed/stored | Understand confidential, sensitive, clinical or regulated data | Data inventory, data flows | Data inventory / Privacy docs | App ownership/business function known | BR | Security, Privacy, DDIT | Security, Privacy, Data Owners, App SMEs | Review data per application | Data classification view | TBD | TBD | TBD | Yes | Data Owner/Privacy | Privacy/security gaps | Data classification artifact | Not Started
48 | 2026-07-27 | User access model | Security | Role-based access setup | Review roles, approvals, recertification | Role matrix, user list, approver list | IAM / App admin exports | App inventory complete | DDIT | BR, Security, Quality | Security, App SMEs, DDIT, Quality | Access lifecycle review | Access model baseline | TBD | TBD | TBD | Yes | Security/DDIT | Access control gaps | Access model knowledge | Not Started
49 | 2026-07-27 | Privileged/vendor access | Security | Admin and third-party access | Review vendor/admin access risks and controls | Privileged user list, vendor access list | IAM / PAM / App admin exports | User access model available | DDIT | CTS, Security | Security, CTS, DDIT, App SMEs | High-risk access review | Privileged access risk list | TBD | TBD | TBD | Yes | Security | Unauthorized access risk | Privileged access artifact | Not Started
50 | 2026-07-27 | Vulnerability status | Security | Open vulnerabilities | Review open vulnerabilities, exceptions, patch risks | Vulnerability reports, scan results | Security tools / Vuln scanner | Infrastructure details available | DDIT | Security, CTS, Infra | Security, Infra, CTS, DDIT | Risk-based review | Vulnerability action log | TBD | TBD | TBD | Yes | Security/DDIT | Security exposure remains open | Vulnerability knowledge | Not Started
51 | 2026-07-27 | Patch management | Security / Operations | Patch process and ownership | Define future patch governance | Patch calendar, patch evidence | Infra tracker / Patch tool | Infrastructure ownership known | DDIT | Infra, CTS, Security | Infra, CTS, DDIT, Security | Patch lifecycle review | Patch governance model | TBD | TBD | TBD | Yes | DDIT Infra | Operational/security risk | Patch process knowledge | Not Started
52 | 2026-07-27 | Logging/security monitoring | Security | Logs, SIEM, alerting | Confirm security logging and monitoring needs | Log architecture, retention details | SIEM / App logs / Security docs | Architecture and hosting known | DDIT | Security, CTS | Security, DDIT, CTS | Security monitoring review | Security monitoring requirements | TBD | TBD | TBD | No | Security | Limited incident detection | Security monitoring artifact | Not Started
53 | 2026-07-27 | Data privacy | Privacy | Privacy obligations | Identify personal/sensitive data and controls | Privacy assessment, data flows | Privacy repository | Data classification complete | BR | Privacy, Security, DDIT | Privacy, Security, Business | Privacy control review | Privacy requirement log | TBD | TBD | TBD | Yes | Privacy/Data Owner | Privacy non-compliance risk | Privacy knowledge | Not Started
54 | 2026-07-27 | Security readiness sign-off | Security / Governance | Minimum security readiness for Oct 1 | Define security transition gate | Draft sign-off criteria | Security readiness tracker | Security topics reviewed | DDIT | Security, Quality, CTS | Security, DDIT, Quality, CTS | Agree readiness criteria | Security readiness checklist | TBD | TBD | TBD | Yes | Security/DDIT | Cutover blocked or unsafe | Security readiness criteria | Not Started
DR

## OCM, Stakeholder Readiness & Bu
Sl No | Planned Date | Topic | Topic Category | Description / Details Needed | Workshop Discussion Focus | Upfront Data to Gather | Data Source / Location | Dependency / Pre-requisite | Primary Owner | Supporting Teams | Stakeholders Required for Workshop | How Discussion Will Be Run | Expected Output | Primary SME | Backup SME | Availability | Decision Required | Decision Owner | Risk if Delayed | Knowledge Artifact for Agent | Status | Comments
55 | 2026-07-29 | Stakeholder mapping | OCM | Impacted stakeholder groups | Identify who is impacted | Stakeholder list, user groups, SMEs | Org charts / App SME list | Application ownership available | BR | DDIT, CTS | BFFs, BR Ops, Business Owners, DDIT, CTS | Map by stakeholder group | Stakeholder map | TBD | TBD | TBD | No | BR OCM Lead | Missing stakeholder engagement | Stakeholder graph | Not Started
56 | 2026-07-29 | Change impact assessment | OCM | What changes for each group | Identify role, process, tooling and escalation changes | Current ways of working, pain points | SME inputs / Process docs | Stakeholder map available | BR | DDIT, CTS | BFFs, OCM Lead, Business Owners | From-to impact discussion | Change impact assessment | TBD | TBD | TBD | No | BR OCM Lead | Adoption gaps | Change impact knowledge | Not Started
57 | 2026-07-29 | BR business ownership model | OCM / Governance | BR retained responsibilities | Confirm business ownership, prioritization, requirements | Current ownership and approval model | Ownership tracker | Ownership baseline complete | BR | DDIT | Business Owners, BFFs, BR Leadership | Clarify retained accountability | BR business ownership model | TBD | TBD | TBD | Yes | BR Leadership | Accountability confusion | Business ownership model | Not Started
58 | 2026-07-29 | New ways of working | OCM | How stakeholders engage after Oct 1 | Support requests, escalations, project requests, approvals | Current process and pain points | Process docs / SME input | Target support model drafted | BR | DDIT, CTS | BR, DDIT, CTS, Business | User journey walkthrough | New ways-of-working guide | TBD | TBD | TBD | Yes | BR/DDIT Leads | Stakeholder confusion post-cutover | Ways-of-working guide | Not Started
59 | 2026-07-29 | Communication strategy | OCM | Who needs to know what and when | Define audience, message, timing, sender, channel | Audience list, key messages | OCM tracker | Stakeholder map available | BR | DDIT, CTS | OCM, BFFs, BR/DDIT Comms | Audience-based planning | Communication plan | TBD | TBD | TBD | No | BR OCM Lead | Delayed adoption | Communication knowledge | Not Started
60 | 2026-07-29 | Training needs | OCM | Training and awareness requirements | Identify who needs process/tool/role training | Role mapping, process changes | OCM tracker / Target process docs | New ways of working drafted | BR | DDIT, CTS | OCM, DDIT, CTS, Business SMEs | Role-based needs analysis | Training plan | TBD | TBD | TBD | No | BR/DDIT OCM Leads | Readiness gaps | Training knowledge | Not Started
61 | 2026-07-29 | Business readiness | OCM | Readiness to operate in new model | Assess readiness concerns and adoption risks | Stakeholder feedback, business calendar | Business inputs | Change impacts identified | BR | Business Owners, DDIT | BFFs, Business Owners, OCM | Readiness criteria discussion | Business readiness checklist | TBD | TBD | TBD | Yes | BR Business Lead | Business disruption risk | Business readiness model | Not Started
62 | 2026-07-29 | Business continuity windows | OCM / Operations | Critical periods to avoid disruption | Capture blackout periods and business deadlines | Business calendar, critical activities | Business calendar | Business owners identified | BR | DDIT, CTS | Business Owners, BFFs, BR Ops | Identify high-risk windows | Business continuity calendar | TBD | TBD | TBD | Yes | BR Business Owner | Cutover may conflict with critical events | BCP calendar knowledge | Not Started
63 | 2026-07-29 | Hypercare handholding | OCM / Operations | Post-cutover support for users | Define duration, channels, issue resolution, office hours | Expected concerns, support availability | OCM/support tracker | Hypercare model drafted | BR | DDIT, CTS | BR, DDIT, CTS, OCM | Define cutover support model | Handholding plan | TBD | TBD | TBD | No | BR/DDIT Leads | Poor adoption after Oct 1 | Hypercare support knowledge | Not Started

## Technology Initiatives, Deliver
Sl No | Planned Date | Topic | Topic Category | Description / Details Needed | Workshop Discussion Focus | Upfront Data to Gather | Data Source / Location | Dependency / Pre-requisite | Primary Owner | Supporting Teams | Stakeholders Required for Workshop | How Discussion Will Be Run | Expected Output | Primary SME | Backup SME | Availability | Decision Required | Decision Owner | Risk if Delayed | Knowledge Artifact for Agent | Status | Comments
64 | 2026-07-30 | Initiative inventory | Delivery | Complete list of linked initiatives | Identify ongoing, in-flight and planned work for each app | Project/demand list, roadmap, backlog | Jira / Portfolio tracker / PMO reports | Application list validated | BR | DDIT, CTS | BR Portfolio, BFFs, App SMEs, DDIT Delivery | Link initiatives to applications | Initiative inventory | TBD | TBD | TBD | No | BR Portfolio | Initiatives may be missed | Portfolio metadata | Not Started
65 | 2026-07-30 | Ongoing initiatives | Delivery | Work actively in execution | Review ownership, progress, risk and transition need | Status reports, project plans, RAID logs | PMO tracker / Jira / Project docs | Initiative inventory available | BR | DDIT, CTS | BR PMs, DDIT Delivery, CTS, Business | Initiative-by-initiative review | Ongoing transition view | TBD | TBD | TBD | Yes | BR/DDIT Delivery | Delivery disruption | Ongoing initiatives knowledge | Not Started
66 | 2026-07-30 | In-flight initiatives | Delivery | Work started but not stable/complete | Decide transfer, joint ownership, pause or revalidate | Current phase, scope, dependencies | Project docs / Jira | Initiative inventory available | BR | DDIT, CTS | BR Delivery, DDIT Delivery, Business | Review phase and risk | In-flight transition approach | TBD | TBD | TBD | Yes | BR/DDIT Delivery | Ownership confusion | In-flight initiative artifact | Not Started
67 | 2026-07-30 | Planned initiatives | Delivery | Demand not yet started | Decide if routed to DDIT intake or reprioritized | Business case, demand backlog, funding status | Demand tracker / Portfolio backlog | Initiative inventory available | BR | DDIT | Business Owners, BR Portfolio, DDIT | Prioritization/intake discussion | Planned demand disposition | TBD | TBD | TBD | Yes | BR Business/DDIT Portfolio | Future work bypasses new model | Planned demand knowledge | Not Started
68 | 2026-07-30 | Enhancement backlog | Delivery | Small changes/enhancements | Decide treatment of open enhancement backlog | Enhancement list, priorities, value | Jira backlog / Demand tracker | Initiative inventory available | DDIT | BR, CTS | BR, DDIT, CTS, Business | Review and categorize backlog | Enhancement transition backlog | TBD | TBD | TBD | Yes | DDIT Delivery | Backlog ownership unclear | Enhancement backlog knowledge | Not Started
69 | 2026-07-30 | Delivery ownership model | Delivery / Governance | Future delivery accountability | Clarify BR priority vs DDIT delivery ownership | Current delivery RACI | Portfolio governance docs | Ownership model discussed | DDIT | BR, CTS | BR Portfolio, DDIT Delivery, CTS | RACI discussion | Delivery ownership model | TBD | TBD | TBD | Yes | DDIT/BR Leads | Project accountability gaps | Delivery ownership graph | Not Started
70 | 2026-07-30 | Initiative takeover approach | Delivery | How DDIT accepts ownership | Direct transfer, joint transition, revalidate, defer, close | Initiative status and risks | Initiative tracker | Initiative inventory complete | DDIT | BR, CTS | BR Delivery, DDIT Delivery, Business | Assign takeover route per initiative | Initiative decision log | TBD | TBD | TBD | Yes | DDIT Delivery | Transition of initiatives stalls | Initiative transition decisions | Not Started
71 | 2026-07-30 | Future demand intake | Delivery / Governance | Process for new requests | Define how BR raises future operations/project asks | Current demand process, pain points | Demand intake tracker | Delivery ownership model drafted | DDIT | BR, CTS | BR, DDIT, Business, CTS | Design intake workflow | Future intake process | TBD | TBD | TBD | Yes | DDIT Portfolio | Future requests unmanaged | Demand intake knowledge | Not Started
72 | 2026-07-30 | Prioritization model | Delivery / Governance | How demand is prioritized | Define business, compliance, funding and capacity criteria | Existing prioritization criteria | Portfolio governance docs | Future intake drafted | BR | DDIT | BR Business, DDIT Portfolio | Define prioritization logic | Demand prioritization model | TBD | TBD | TBD | Yes | BR Business/DDIT Portfolio | Misaligned priorities | Prioritization framework | Not Started

## Contracts, Vendor, Finance & Bu
Sl No | Planned Date | Topic | Topic Category | Description / Details Needed | Workshop Discussion Focus | Upfront Data to Gather | Data Source / Location | Dependency / Pre-requisite | Primary Owner | Supporting Teams | Stakeholders Required for Workshop | How Discussion Will Be Run | Expected Output | Primary SME | Backup SME | Availability | Decision Required | Decision Owner | Risk if Delayed | Knowledge Artifact for Agent | Status | Comments
73 | 2026-07-31 | Existing BR-CTS SOW scope | Finance / Vendor | Current contractual coverage | Review whether SOW covers required transition work | Signed SOW, service scope, exclusions | Procurement repository / Contract folder | Scope baseline available | BR | CTS, Procurement, DDIT | BR Vendor Mgmt, CTS, Procurement, DDIT | SOW vs future need review | SOW gap assessment | TBD | TBD | TBD | Yes | BR/DDIT Vendor Mgmt | Contract gaps delay execution | SOW knowledge artifact | Not Started
74 | 2026-07-31 | DDIT-CTS vendor model | Vendor | Existing DDIT vendor structure | Understand how CTS operates for DDIT today | DDIT managed service contract summary | DDIT vendor repository | BR-CTS SOW reviewed | DDIT | CTS, Procurement | DDIT Vendor Mgmt, CTS, Procurement | Compare BR and DDIT models | Vendor alignment view | TBD | TBD | TBD | Yes | DDIT Vendor Mgmt | Misaligned vendor model | Vendor operating model | Not Started
75 | 2026-07-31 | Contractual gaps | Finance / Vendor | Missing contractual coverage | Identify gaps for KT, remediation, tooling, projects | SOW, MSA, commercials | Procurement/legal repository | SOW/vendor model reviewed | DDIT | BR, CTS, Procurement | Procurement, Legal if needed, CTS, DDIT | Contract gap discussion | Contract change log | TBD | TBD | TBD | Yes | Procurement/DDIT | Required work may not be covered | Contract gap knowledge | Not Started
76 | 2026-07-31 | Commercial model | Finance | One-time and recurring costs | Define transition, remediation, BAU, project cost categories | Current budget, rate cards, assumptions | Finance tracker / Vendor rate cards | Workstream scope drafted | BR | DDIT, CTS, Finance | Finance, Procurement, BR/DDIT, CTS | Cost category discussion | Commercial model options | TBD | TBD | TBD | Yes | Finance/BR/DDIT | Budget not approved in time | Commercial model knowledge | Not Started
77 | 2026-07-31 | Budget ownership | Finance | BR vs DDIT funding responsibility | Clarify cost center and budget boundary | Cost centers, budget ownership | Finance systems / Budget tracker | Commercial model drafted | BR | DDIT, Finance | Finance, BR Leadership, DDIT Leadership | Funding boundary discussion | Budget ownership model | TBD | TBD | TBD | Yes | BR/DDIT Finance | Funding ambiguity | Budget ownership artifact | Not Started
78 | 2026-07-31 | Cost estimate approach | Finance | Estimation methodology | Define how budget estimates will be created | Effort assumptions, resource estimates | PMO tracker / CTS estimates | Workstream plans drafted | DDIT | BR, CTS, Finance | Finance, PMO, CTS, DDIT | Define estimate template | Budget estimate framework | TBD | TBD | TBD | Yes | Finance/PMO | LT cannot approve investment | Cost estimate model | Not Started
79 | 2026-07-31 | Resource capacity | Finance / Delivery | People required for execution | Identify SME, DDIT, CTS, Quality, PMO capacity | Resource availability, effort needs | Resource tracker | Workstream plans drafted | DDIT | BR, CTS, Quality | PMO, BR, DDIT, CTS, Quality | Capacity planning discussion | Resource plan | TBD | TBD | TBD | Yes | PMO/DDIT | Execution delays | Resource capacity artifact | Not Started
80 | 2026-07-31 | Licensing/subscriptions | Finance / Vendor | Software/license ownership | Confirm owner, renewal, transfer need | License inventory, renewal dates, contracts | Procurement repository / License tracker | Application inventory complete | BR | DDIT, Procurement | Procurement, App Owners, DDIT | Review license obligations | License ownership map | TBD | TBD | TBD | No | Procurement | License/support risk | License knowledge | Not Started
81 | 2026-07-31 | Third-party vendors | Vendor | Vendors other than CTS | Identify contracts and dependencies | Vendor list, contracts, POs | Procurement repository | App inventory complete | BR | DDIT, Procurement | Procurement, BR Ops, DDIT | App-by-app vendor review | Third-party vendor map | TBD | TBD | TBD | No | Procurement | Vendor dependency missed | Vendor dependency graph | Not Started
82 | 2026-07-31 | Budget approval path | Finance / Governance | Approval process and timing | Define who approves funding and when | Budget governance process | Finance governance docs | Budget estimate approach drafted | BR | DDIT, Finance | Finance, BR/DDIT Leads | Define approval flow | Budget decision path | TBD | TBD | TBD | Yes | Finance/Leadership | Funding approval delay | Budget approval workflow | Not Started

## Future Operating Governance & D
Sl No | Planned Date | Topic | Topic Category | Description / Details Needed | Workshop Discussion Focus | Upfront Data to Gather | Data Source / Location | Dependency / Pre-requisite | Primary Owner | Supporting Teams | Stakeholders Required for Workshop | How Discussion Will Be Run | Expected Output | Primary SME | Backup SME | Availability | Decision Required | Decision Owner | Risk if Delayed | Knowledge Artifact for Agent | Status | Comments
83 | 2026-08-03 | BR-DDIT-CTS RACI | Governance | Role clarity across parties | Define BR business ownership, DDIT ops/delivery ownership, CTS execution | Draft RACI, current roles | PMO tracker / Operating model docs | Scope, ops, delivery models drafted | DDIT | BR, CTS | BR, DDIT, CTS, Business Owners | RACI walkthrough | Approved RACI | TBD | TBD | TBD | Yes | BR/DDIT Leads | Accountability confusion | RACI knowledge graph | Not Started
84 | 2026-08-03 | Governance forums | Governance | Future operating forums | Define service, portfolio, remediation and escalation forums | Current governance cadence | PMO docs | RACI drafted | DDIT | BR, CTS, Quality | BR/DDIT Leads, CTS, PMO | Define forum purpose and cadence | Governance calendar | TBD | TBD | TBD | Yes | BR/DDIT Leads | Model not sustained post-Oct | Governance calendar artifact | Not Started
85 | 2026-08-03 | Decision rights | Governance | Who decides what | Scope, budget, remediation, prioritization, exceptions | Current decision model | PMO / Leadership inputs | Governance forums drafted | BR | DDIT, Finance, Quality | BR/DDIT Leadership, Finance, Quality | Decision mapping | Decision rights matrix | TBD | TBD | TBD | Yes | BR/DDIT Leadership | Slow or unclear decisions | Decision framework | Not Started
86 | 2026-08-03 | RAID governance | Governance | Risk, issue, dependency tracking | Define RAID ownership, cadence and escalation | Initial RAID register | PMO tracker | Workstream risks identified | DDIT | BR, CTS | PMO, Workstream Leads | Define RAID process | RAID management process | TBD | TBD | TBD | No | PMO | Risks not escalated | RAID knowledge | Not Started
87 | 2026-08-03 | Transition acceptance criteria | Governance / Operations | Conditions to accept ownership | Define minimum acceptance checklist by app/category | Draft acceptance criteria | Readiness tracker | Ops/compliance/security topics reviewed | DDIT | BR, CTS, Quality, Security | DDIT, BR, CTS, Quality, Security | Readiness gate discussion | Acceptance checklist | TBD | TBD | TBD | Yes | DDIT/Quality | Unsafe or disputed handover | Acceptance criteria artifact | Not Started
88 | 2026-08-03 | Residual action governance | Governance / Remediation | Post-Oct open actions | Define ownership and tracking for residual items | Open action list, remediation backlog | Remediation tracker / RAID | Remediation plan drafted | DDIT | BR, Quality | PMO, Quality, DDIT, BR | Governance design | Residual action tracker | TBD | TBD | TBD | Yes | DDIT/Quality | Residual gaps not governed | Residual action model | Not Started
89 | 2026-08-03 | Reporting and dashboards | Governance | Program reporting needs | Define LT and working-level reporting | Existing reports, desired KPIs | PMO / Dashboards | Governance forums drafted | DDIT | BR, CTS | PMO, Sponsors, Workstream Leads | Define reporting structure | Reporting framework | TBD | TBD | TBD | No | PMO | Poor leadership visibility | Reporting knowledge | Not Started
90 | 2026-08-03 | Success criteria | Governance | What success looks like | Define measurable transition success | Initial success measures | PMO / Leadership inputs | Acceptance criteria drafted | BR | DDIT | BR/DDIT Leadership, PMO | Agree success measures | Success criteria | TBD | TBD | TBD | Yes | BR/DDIT Leadership | Misaligned expectations | Success criteria artifact | Not Started
91 | 2026-08-03 | Closure criteria | Governance | When transition program closes | Define BAU handover and closure conditions | Draft closure checklist | PMO tracker | Success criteria agreed | DDIT | BR, CTS | PMO, BR/DDIT/CTS Leads | Define closure requirements | Program closure criteria | TBD | TBD | TBD | Yes | BR/DDIT Leads | Program may drag without closure | Closure criteria artifact | Not Started